## Start
e-Health Implementation Toolkit (e-HIT)
A guide for Senior Managers to Implementing e-Health initiatives in the NHS
Elizabeth Murray
Carl May
Frances Mair
Enter the Toolkit
Background and Instructions
If this is the first time you’ve seen the e-HIT, you may want to read the instructions and learn more about how to use it, and how it was developed. Click on the Background and Instructions tab for this. If you already know how to use it, go straight to the toolkit itself, or if you have already completed it, you can go straight to the report.
Report
Toolkit built by Rocket Science UK Ltd
© The e-HIT is jointly owned by Elizabeth Murray, Carl May and Frances Mair (content) and Rocket Science UK Ltd (tool).

## Introduction
Introduction
What is the e-HIT?
The e-HIT is an e-Health Implementation Toolkit. It is a guide to help decide whether to embark on an e-Health implementation initiative. If you do decide to go ahead, it will help you identify the strengths of the organisation and intervention along with any potential pitfalls and problems which you may encounter.
An e-Health initiative is any initiative which uses Information and Communication Technologies in a health service context – this might be Choose and Book, Picture Archiving and Communication System, an Electronic Health Record, electronic prescribing, a new Patient Administration System, telemedicine or any other initiative that uses ICT.
Who should use this e-HIT?
Anyone involved in deciding whether to embark on implementing an e-Health initiative, or in planning or undertaking its implementation. It is probably best to get several people from different professional backgrounds to use the e-HIT and compare notes, for example doctors and managers may have different views on the effect of the proposed technology on clinical interaction.
When should the e-HIT be used?
The e-HIT can be used at various points during an implementation. We advise using it at the beginning, as a way of sensitising yourself to the multiple issues you are likely to encounter. You may also want to use it during the planning and implementation process, to review how far you have got, or to consider reasons for unexpected difficulties or delays.
How should the e-HIT be used?
The e-HIT is a sensitising tool not a simplistic tick-box or check-list. Senior managers have a wealth of experience and expertise and a simplistic approach would be unhelpful. The e-HIT presents the major factors which we believe need consideration, and possible action, in order for a new technology to be successfully integrated into routine practice. It’s unlikely that any one person will have all the answers to all the questions, so you may want several people to complete the tool independently or together as a team.
We have provided information buttons to clarify some of the questions (which are revealed if you hover your mouse over the right hand side statement for each question) and Case Studies to show worked examples.
Next page
Introduction
Background
Instructions
Case Studies
Empirical and Theoretical Basis to the e-HIT
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)

## Background
Background
The National Health Service (NHS) in the UK is implementing the largest IT programme ever. Not surprisingly, different parts of the programme have progressed at different rates, with some e-Health applications rapidly integrating into existing working patterns, while others appear to remain endlessly on the horizon, causing much frustration and wasted resources.
Health care organisations, whether a single GP practice, a Primary Care Trust, a hospital trust or an entire Regional Health Authority, are highly complex systems. As such, a seemingly small change in one area can have multiple, apparently unpredictable effects, in some quite different parts of the organisation.
We have simplified this e-HIT into three component parts:
For more about the derivation e-HIT, please see the section on the empirical and theoretical basis to the e-HIT.
Next page
• The overall context.
This includes considerations at national level like the Connecting for Health (CfH) programme, nationally set targets or priorities, and at organisational level such as existing leadership, locally determined targets, business plans and budgets.
• The e-Health intervention.
This might be a nationally driven programme like PACS (Picture Archiving and Communication System) or Choose and Book, or a locally inspired initiative aimed at solving a local problem.
• The workforce (people and workpatterns).
This includes staff who will have to use the intervention, staff who may not have to directly use the intervention, but whose workload or workflow may be affected, and patients.
Introduction
Background
Instructions
Case Studies
Empirical and Theoretical Basis to the e-HIT
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)
Go back

## Instructions
Step-by-step instructions
Step 1: Save the Tool
Save a new version of the e-HIT (File/Save As...) on your computer. Remember to press Save (File/Save) at regular intervals while you are using the tool.
Step 2: Enter the Tool
On the first page, you can click the button to ‘Enter the tool-kit’ or view more detailed background information and instructions in the introduction section. You can then use the buttons at the top of the page to navigate through the toolkit.
Step 3: Six assessment pages
The assessment part of the e-HIT has six pages:
i) Context (1)
ii) Context (2)
iii) Context (3)
iv) Intervention
v) Workforce (1)
vi) Workforce (2)
You can move between the pages by using the buttons at the top of the page, or by using the buttons provided at the end of each section.
Step 4: Scoring and providing evidence
Each assessment page is broken down into several topics. Give your e-Health intervention a score for each topic by choosing a position on the bar that, from your perspective, represents its current position. If you have trouble using the sliding scale, you can click on the number below the bar and enter a score from 0 – 10. Note that this is set to a default score of 5. If you feel unable to score a particular question, you may wish to discuss the question with others, or leave it at the default. Guidance notes are shown for each topic if you hover your mouse over the right hand side statement.
For each score you record, please add the reasons for your judgement (this will be useful for any subsequent review of your intervention or for sharing your e-HIT results with colleagues) as well as a reference to any supporting evidence (this might include outcome/performance figures, monitoring data, names of relevant documents/strategies etc). The boxes provided do not expand so please be concise.
Step 5: Next page
Move to the next page, assess your organisation/project and arrive at a score; provide any supporting evidence for your judgement. Continue on through all six assessment pages of the e-HIT.
Step 6: Reviewing your scores
Once you have completed the six assessment pages, the e-HIT automatically generates a summary report of all your scores, with accompanying graphs to help you to see the strengths and weaknesses of your e-Health intervention.
Step 7: Print
When you have completed the exercise, print all the pages you wish to by selecting File/Print. You may want to circulate the scores and summary report to colleagues, particularly those detailed with specific tasks and responsibilities.
Next page
Introduction
Background
Instructions
Case Studies
Empirical and Theoretical Basis to the e-HIT
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)
Go back

## Further Info
Empirical and Theoretical Basis and sources of further information.
In 2006 the Service Delivery and Organisation (SDO) stream of the National Institute for Health Research (NIHR) funded a two-year research project to identify the barriers and facilitators to implementation of e-Health initiatives within the NHS. This e-Health Implementation Toolkit is a product of this research project.
There were four Work Packages (WP) to the project. Our first task, addressed in Work Package 1 (WP1) was to identify and summarise all the existing literature on e-Health implementation. In order to do this, we undertook a review of reviews, using systematic review methods to identify all existing reviews addressing this subject. We subsequently synthesised the findings of the reviews, and provided a summary of the factors thought to be important in implementing e-Health initiatives in the literature.
Two of the other work packages (WP2 and WP4) used qualitative methods to explore health professional (WP2) and implementer (WP4) views on barriers and facilitators to implementing e-Health initiatives within the NHS. The data from WP4 were particularly pertinent to developing this e-HIT, and were also used in completing the case studies.
The entire project was informed by May’s Normalisation Process Model (NPM). This is a sociological theory which describes why certain e-Health technologies “normalise” and become part of every day routine practice, and others do not. It proposes that there are four constructs which determine normalisation, and these are interactional workability (the impact of the new technology on the interactions between health professionals and patients); relational integration (the impact of the new technology on the relations, including trust and respect, between different groups of workers); skill set workability (the degree to which the new technology fits with existing skill sets); and contextual integration (the impact of the new technology on the organisation as a whole). Details of the NPM are available at:
http://www.biomedcentral.com/1472-6963/6/86
http://www.biomedcentral.com/1472-6963/7/148
Readers who are interested in learning more about the empirical basis to the e-HIT are directed to the report of the research project, located on the SDO website (insert link when available). The following publications in peer reviewed journals report specific components of the overall project:
Mair F, May C, Murray E, Finch T, O'Donnell C, Anderson G et al…
Understanding the implementation and integration of e-Health Services. Report for the NHS Service
and Delivery R&D Organisation (NCCSDO). 2009. London, SDO.
http://www.sdo.nihr.ac.uk/files/project/135-final-report.pdf
Introduction
Background
Instructions
Case Studies
Empirical and Theoretical Basis to the e-HIT
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)
Next page
Go back

## Case Studies
Case Studies
Three case studies have been prepared using the e-HIT. You can download these case studies from the internet using the links below.
Choose and Book
We studied Choose and Book in an early adopter site, consisting of one hospital and one PCT that referred to that hospital.
Download the Choose and Book Case Study
Community Nursing Information System
We studied a Community Nursing Information System (CNIS) in one Health Board in Scotland. The CNIS was designed to provide an electronic patient record system for District Nurses to enable them to record and deliver information to support the delivery of care to patients, and to interface with and share information with associated agencies, particularly Social Services. A web-based electronic system in conjunction with a hand held mobile device (iPAQ) enabled staff to gather and share information electronically.
Download the CNIS Case Study
Picture Archiving and Communication System (PACS)
The final case study looks at the implementation of the Picture Archiving and Communication System (PACS) in a Foundation Trust hospital. PACS is a system that allows digital recording of X-Rays and other images, which means the images can be transferred electronically, and hence shared between different clinicians in different places.
Download the PACS Case Study
Introduction
Background
Instructions
Case Studies
Empirical and Theoretical Basis to the e-HIT
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)
Toolkit
Go back

## Context1
Policy
National policy | This intervention is completely at odds with current or planned national policy. |  | This intervention is entirely compatible with current and planned national policy.
5
Add the reasons for your score and accompanying evidence here
| This intervention will hinder the achievement of nationally directed priorities or targets. |  | This intervention will enable the achievement of nationally directed priorities or targets.
5
Add the reasons for your score and accompanying evidence here
Local policy | This intervention is completely at odds with current or planned local policies. |  | This intervention is entirely compatible with all current and planned local policies.
5
Add the reasons for your score and accompanying evidence here
Note on E10: Think about Connecting for Health, Choice, and other flagship NHS policies.
Note on E13: Will the intervention help you achieve targets like waiting list targets? You may also want to think about the cost of NOT implementing this initiative, in terms of not being able to meet targets.
Note on E16: Local policies often differ from national policies, as they reflect local priorities. Local policies may be at the level of the trust (PCT, community or hospital) or organisation (General Practice, district nursing team, hospital).
Context (1)
No man is an island, and neither is any NHS organisation. Before deciding whether or not to implement a new intervention, it is worth considering the overall context, and in particular, how well the intervention will fit with organisational priorities and structures. In turn, these are often influenced by national policies.
Next page
Context (1)
Context (2)
Context (3)
Intervention
Workforce (1)
Workforce (2)
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)

## Context2
Culture
Local culture | The organisational culture is reluctant to adopt e-Health initiatives and dreads change. |  | The organisational culture welcomes e-Health initiatives and embraces change.
5
Add the reasons for your score and accompanying evidence here
| The multiple staff groups likely to be involved in implementing the e-Health initiative have poor working relationships and poor communication with no history of problem solving and co-operation. |  | The multiple staff groups likely to be involved in implementing the e-Health initiative have good working relationships and good communication with a history of problem solving and co-operation.
5
Add the reasons for your score and accompanying evidence here
| There is no local sponsor, or the local sponsor is not well respected, or is likely to devote insufficient time and energy to promoting the implementation. |  | The intervention is strongly supported by a well-respected local sponsor who will provide the time and energy needed to promote the implementation.
5
Add the reasons for your score and accompanying evidence here
| There are particular opinion leaders within the organisation who are likely to oppose implementation of this e-Health initiative. |  | There are particular opinion leaders within the organisation who are likely to support the implementation of this e-Health initiative.
5
Add the reasons for your score and accompanying evidence here
Note on E10: It may be helpful to think of multiple sub-cultures within the organisation – for example the nurses may welcome innovation while the doctors may resist it. You will need to give an overall score, but you can highlight problem areas in the text below.
Note on E13: Try to think of ALL the staff groups who are likely to be impacted. It’s easy to forget some of the less front-line staff, but if their work patterns are going to be affected, they will have to be involved.
Note on E16: A sponsor is not the same as an opinion leader (next question). A sponsor is a person who wants to see this initiative implemented, and is happy to drive it forward, either directly, or by delegation.
Note on E19: e.g. a powerful clinician who carries the respect of other clinical staff. This may counterbalance the impact of a respected sponsor.
Context (2)
Next page
Context (1)
Context (2)
Context (3)
Intervention
Workforce (1)
Workforce (2)
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)
Go back

## Context3
Resources and risk
Resources | The organisation is under resourced, and cannot fully meet the costs and additional workload resulting from the implementation of this e-health initiative, including e.g. training, on-going support, contingencies, publicity. |  | The organisation is well resourced, and can fully meet the costs and additional workload resulting from the implementation of this e-health initiative, including e.g. training, on-going support, contingencies, publicity.
5
Add the reasons for your score and accompanying evidence here
| The e-Health initiative is likely to disrupt the existing allocation of resources or the formal or informal norms by which they are allocated. |  | The e-Health initiative will make no change to existing allocation of resources or the formal or informal norms governing allocation of resources.
5
Add the reasons for your score and accompanying evidence here
Risk | The proposed intervention is completely at odds with the organisation’s existing risk management policies. |  | The proposed intervention is entirely compatible with the organisation’s existing risk management policies.
5
Add the reasons for your score and accompanying evidence here
Note on E10: Think here about costs incurred during preparation for the implementation, the implementation, and after the implementation. Will there be a period of running two systems in parallel? There may need to be pump-priming funding to meet up-front costs, even if in the long run, the initiative is designed to reduce costs.
Note on E13: This is about the ways resources (money, staff, prestige, time, space) are allocated. Even more important that the overt, official methods of allocation are the informal expectations and norms that have developed over the years.
Note on E16: Think here about the compatibility of the initiative with risk management policies of the organisation overall, not about whether the initiative increases or decreases risk itself.
Context (3)
Next page
Context (1)
Context (2)
Context (3)
Intervention
Workforce (1)
Workforce (2)
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)
Go back

## Intervention
Intervention
Impact on clinical practice | The e-Health initiative will disrupt health professional – patient interactions. E.g. it will make them slower, or introduce tasks inappropriate to the encounter. |  | The e-Health initiative will facilitate health professional – patient interactions. E.g. it improves communication within consultations, or enables faster completion of the key objectives of health care interactions.
5
Add the reasons for your score and accompanying evidence here
| There are serious concerns about the reliability, security and confidentiality of the intervention. |  | The intervention is entirely credible in terms of security, confidentiality and reliability.
5
Add the reasons for your score and accompanying evidence here
Ease of use of the system | The e-Health initiative is difficult to use, or does not do what it’s supposed to do. |  | The e-Health initiative is easy to use and fit for purpose.
5
Add the reasons for your score and accompanying evidence here
Effectiveness and cost-effectiveness | The e-Health initiative has not been evaluated nor demonstrated to improve health care in a cost-effective manner. |  | The e-Health initiative has been well evaluated and has been demonstrated to improve health care in a cost-effective manner.
5
Add the reasons for your score and accompanying evidence here
Note on E10: It may be hard for a manager to answer this – but clinicians will have strong views.
Note on E13: These concerns may be objective or subjective.
Note on E16: A technology that has been designed in consultation with end-users or can be easily adapted to local needs is likely to be more user friendly and fit for purpose.
Note on E19: The evaluation could be high quality RCT evidence, or it could be locally respected experience.
The Intervention
The nature of the intervention is likely to be a key factor in whether it is successfully integrated into routine practice or not.
Next page
Context (1)
Context (2)
Context (3)
Intervention
Workforce (1)
Workforce (2)
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)
Go back

## Workforce
Workflow and training
Impact on work and workflow | There is likely to be a period of considerable increased workload during the implementation. |  | There is unlikely to be any period of increased workload during the implementation.
5
Add the reasons for your score and accompanying evidence here
| The intervention will disrupt existing work patterns and make them less efficient. |  | The intervention will increase the efficiency of current work patterns.
5
Add the reasons for your score and accompanying evidence here
| The intervention will substantially disrupt current divisions of labour between staff groups. |  | The intervention is completely compatible with current divisions of labour.
5
Add the reasons for your score and accompanying evidence here
Education and training | All staff who will use the proposed initiative will need very substantial training prior to use. |  | No training will be needed by any staff group prior to implementation of the initiative.
5
Add the reasons for your score and accompanying evidence here
Note on E10: e.g. as staff learn to use the new technology or contribute to re-engineering workflow patterns, or have to run two systems in parallel.
Note on E13: Think about any re-engineering of work patterns that may be needed.
Note on E16: e.g. makes clinical staff undertake tasks they see as clerical, or clerical staff do work they see as outside their skill set.
Note on E19: It is difficult to conceive of an initiative that needs no training, but think about the amount of training required, how this will be delivered and resourced, and what level of on-going support may be needed.
The workforce - people and work patterns (1)
The workforce, including the various professional groups who are going to have to use the new intervention are crucial in determining whether the intervention becomes embedded into routine practice, or whether it is merely imposed. People may “adopt” a technology – i.e. use it, however much it disrupts their work, if the incentives for use, or the penalties for non-use, are sufficient. Once these incentives or penalties are removed however, they are likely to stop using it. In contrast, a technology that has become “normalised”, or part of routine use, will continue to be used even after the incentive structure has been dismantled.
Next page
Context (1)
Context (2)
Context (3)
Intervention
Workforce (1)
Workforce (2)
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)
Go back

## Workforce2
Relationships
Relationships between different professional groups | The proposed intervention will substantially disrupt existing power relationships between different staff groups. |  | The proposed intervention is entirely compatible with existing power relationships between different staff groups.
5
Add the reasons for your score and accompanying evidence here
| The intervention will undermine confidence about each other’s expertise and performance between different professional groups. |  | The intervention will enhance confidence about each other’s expertise and performance between different professional groups.
5
Add the reasons for your score and accompanying evidence here
| Responsibility and accountability are not aligned, i.e. different staff groups have responsibility for how the intervention is used, and accountability for the outcome of the intervention. |  | Responsibility and accountability are fully aligned i.e. one staff group is both responsible for how the intervention is used and accountable for the outcome of the intervention.
5
Add the reasons for your score and accompanying evidence here
Note on E10: Choose and Book allows GPs to book patients straight into specific clinics, where previously consultants could screen referral letters and divert inappropriate referrals to the correct clinic. This alters the power relationship, as well as impacting on patient flow and the clinical interaction.
Note on E13: Virtual outreach clinics (three-way consultations between the patient, the referring GP, and the Consultant) had both positive and negative impact on this – with some specialists not feeling able to rely on GPs to determine subtle but important signs in a physical examination, while others were reassured by observing the level of competence of participating GPs.
Note on E16: If responsibility and accountability are fully aligned one staff group is both responsible for how the intervention is used and accountable for the outcome of the intervention, while if different staff groups have responsibility for how the intervention is used, and accountability for the outcome of the intervention, they are not aligned.
The workforce - people and work patterns (2)
Report
Context (1)
Context (2)
Context (3)
Intervention
Workforce (1)
Workforce (2)
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)
Go back

## Using the Results
Using the results of the e-HIT
The topics in the e-HIT are intended to act as sensitising tools – only some of the factors will be relevant in any one implementation. No one factor is likely to act as a “deal-breaker”, but in general, the greater the number of potential pitfalls, the less likely it is that the planned intervention will normalise. Negotiation and planning will be needed to overcome resistance to technologies that are likely to disrupt working patterns, relationships between professional groups, existing patterns of communication, and existing distributions of power, status, access to resources and responsibilities.
Interpretation of the results
The results are presented graphically on the next page. The higher the score, the more likely it is that your planned initiative will implement successfully.
The first graph summarises your entries for the context, intervention and workforce. Subsequent graphs look at each of these in more detail. Headings with a low score are areas that you will probably want to look at in more detail, and work out what problems you are likely to face, and what you can do to overcome or avoid the problems. On the subsequent pages, you can view a summary of your comments for each area and also use the final page to note any major issues and potential solutions arising from your interpretation of the results.
Next page
Using the Results
Summary of Scores
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)
Summary of Comments
Issues and Solutions

## Scores
Summary of Topic Scores
Context | 50%
The intervention | 50%
The workforce | 50%
Context
National policy | Compatibility with current and planned national policy | 5
| Enabling the achievement of national priorities or targets | 5
Local policy | Compatibility with current and planned local policy | 5
Local culture | Welcoming e-health / embracing change | 5
| Good working relationships | 5
| Supported by a well-respected local sponsor | 5
| Supported by opinion leaders | 5
Resources | Well resourced | 5
| Minimal impact on resource allocation | 5
Risk | Compatibility with existing risk management policies | 5
50
The Intervention
Impact on clinical practice | Facilitation of health professional - patient interactions | 5
| Security, confidentiality and reliability | 5
Ease of use of the system |  | 5
Effectiveness and cost-effectiveness |  | 5
20
The workforce - people and work patterns
Impact on work and workflow | Not increasing staff workloads | 5
| Increasing efficiency of work patterns | 5
| Compatibility with divisions of labour | 5
Education and training | Minimal training needed | 5
Relationships between different professional groups | Compatibility with existing power relationships | 5
| Enhancing confidence between groups | 5
| Alignment of responsibility and accountability | 5
35
Summary
Context | 50%
The intervention | 50%
The workforce | 50%
Summary of Scores
These scores are subjective and only a guide, however, the higher the scores, the more likely that the intervention will normalise.
Using the Results
Summary of Scores
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)
Summary of Comments
Issues and Solutions
Next page
Go back

## Comments
Context
Topic | Sub-topic | Score | Comments
National policy | Compatibility with current and planned national policy | 5 | Add the reasons for your score and accompanying evidence here
| Enabling the achievement of national priorities or targets | 5 | Add the reasons for your score and accompanying evidence here
Local policy | Compatibility with current and planned local policy | 5 | Add the reasons for your score and accompanying evidence here
Local culture | Welcoming e-Health / embracing change | 5 | Add the reasons for your score and accompanying evidence here
| Good working relationships | 5 | Add the reasons for your score and accompanying evidence here
| Supported by a well-respected local sponsor | 5 | Add the reasons for your score and accompanying evidence here
| Supported by opinion leaders | 5 | Add the reasons for your score and accompanying evidence here
Resources | Well resourced | 5 | Add the reasons for your score and accompanying evidence here
| Minimal impact on resource allocation | 5 | Add the reasons for your score and accompanying evidence here
Risk | Compatibility with existing risk management policies | 5 | Add the reasons for your score and accompanying evidence here
The Intervention
Impact on clinical practice | Facilitation of health professional - patient interactions | 5 | Add the reasons for your score and accompanying evidence here
| Security, confidentiality and reliability | 5 | Add the reasons for your score and accompanying evidence here
Ease of use of the system |  | 5 | Add the reasons for your score and accompanying evidence here
Effectiveness and cost-effectiveness |  | 5 | Add the reasons for your score and accompanying evidence here
The workforce - people and work patterns
Impact on work and workflow | Not increasing staff workloads | 5 | Add the reasons for your score and accompanying evidence here
| Increasing efficiency of work patterns | 5 | Add the reasons for your score and accompanying evidence here
| Compatibility with divisions of labour | 5 | Add the reasons for your score and accompanying evidence here
Education and training | Minimal training needed | 5 | Add the reasons for your score and accompanying evidence here
Relationships between different professional groups | Compatibility with existing power relationships | 5 | Add the reasons for your score and accompanying evidence here
| Enhancing confidence between groups | 5 | Add the reasons for your score and accompanying evidence here
| Alignment of responsibility and accountability | 5 | Add the reasons for your score and accompanying evidence here
Summary of Comments
Using the Results
Summary of Scores
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)
Summary of Comments
Issues and Solutions
Next page
Go back

## Issues
Issue | Potential Solution
Major Issues and Potential Solutions
You can use this section to note any major issues related to implementing your e-Health initiative that are apparent after having used the e-HIT, and describe some potential solutions.
Using the Results
Summary of Scores
Introduction
Toolkit
Report
Start
e-Health Implementation Toolkit (e-HIT)
Summary of Comments
Issues and Solutions
Go back